## Sheet1
Note: Please ensure no personal contact details are included in this register. This register is available for public access from the website.
Name | Incident ID | Date | Time | Method of Complaint Communication | Key site activities occurring at time of complaint and where? (e.g. clearing and extraction in Sector 2) | Key Complaint Issue (e.g. noise, dust, traffic) | Details | Response and Action | Date of Closure
Keiron Rochester | CTR_INC1 | 10.9.2019 | 12:30pm | Phone | Clearing and set up | 1. Work starting times. 2. Site egress. | 1. Query on the starting time of the earthworks crew. 2. Also people working on site on Sunday. 3. Right turn out of site by staff. | 1. Site manager confirmed and days sheets confirm no work commenced prior to 7.00am staff did arrive on site prior to 7.00am. 2. Sunday there was a water cart on site to mange dust control only. 3. Right turn out for trucks is prohibited and is now sign posted, right turn out for passenger vehicles etc is permissible. Darren called back and advised there where no non-compliances | 11.09.2019
Steve Kewins | CTR_INC2 | 12.09.2019 | 9.15am | Phone | No activities on site over the weekend (except for a water cart for dust control) | Dust | 1. Enquiring about dust monitors working, as he noticed dust blowing from the site of an evening over the weekend with high winds. | He was advised the monitors are operating, and we knew we had dust over the weekend that we tried to control. We would be providing notices to residents soon. | 12.09.2019
Shirley Davis | CTR_INC3 | 11.10.2019 | 12.30pm | Phone | Internal roadworks adjacent to weighbridge area | Traffic | 1. Raised concern regarding trucks turning right entering and exiting the site | During civil work vehicles are permitted to enter the site by turning right. Notwithstanding the Quarry Manager contacted the civil works contractor and has directed all contractor heavy vehicles and trucks to enter and exit the site by left turn only. Quarry Manager returned call to complainant and left voice message of actions taken. | 11.10.2019
Kay Rochester | CTR_INC4 | 11.10.2019 | 1.01pm | Phone | Internal roadworks adjacent to weighbridge area | Traffic | 1. Raised concern regarding trucks turning right entering and exiting the site 2. Concerned about traffic passing on the inside of turning trucks with potential for accident. | During civil works, vehicles are permitted to enter the site by turning right. Newcastle Sand has no control over the driving practises of the general public in regards to overtaking. Notwithstanding the Quarry Manager contacted the civil works contractor and has directed all contractor heavy vehicles and trucks to enter and exit the site by left turn only. Quarry Manager returned call to complainant and left voice message of actions taken | 11.10.2019
Barry Davis | CTR_INC5 | 24.10.2019 | 11.46am | Phone | After Hours | Noise | 1. Raised concern regarding a person cutting logs onsite at 8-8.30 pm on 23.10.2019. | Quarry manager investigated and found that another neighbour had cut logs on site for firewood in front of entry gate between 6.00 and 7.00pm. Neighbour has been informed that he is not authorised to cut timber inside property adjacent to roadway. Called complainant back to advise of findings and discussed with son and wife Shirley. | 24.10.2019
Kay Rochester | CTR_INC6 | 24.10.2019 | 2.50pm | Phone | Internal roadworks | Traffic | 1. Kay raised concern that a truck passed her car on the inside to turn left into the mine site, whilst she was stationary awaiting to turn into her driveway. A car travelling behind the truck apparently nearly hit Kay 's car. | Quarry manager immediately contacted the civil construction foreman who questioned the truck driver to get more details. "Truck driver had indicated to turn left and slowed down to enter site and a member of the public has sped past him. Truck driver had sufficient room to safely pass on the inside and the car following was at fault." | 24.10.2019
Department of Planning, Industry & Environment - Complaint received by unknown applicant. | CTR_INC7 | 09.01.2020 | 5.27pm | Email | Construction activies occurring outside approved constructions hours. | Construction hours | 1. A request was made by the Department of Planning, Industry and Environment to provide information for various matters. | A Formal response has been prepared by Newcastle Sand and the Contractor. The response has been forwarded to the Department of Planning, Industry and Environment for consideration. | 20.01.2020
Keiron Rochester | CTR_INC8 | 30.01.2020 | 4.44pm | Email | Westbound vehicle considered turning right into the quarry. | Traffic | 1. The observer believes a vehicle considered to turn right into the quarry. However, they did not turn right in and continued on. The vehicle returned and accessed the quarry via a left turn in. | Incident investigated by Quarry Manager and formal response has been emailed. The vehicle did not turn right into driveway and has been counselled in relation to the complaint. | 14.02.2020
Keiron Rochester | CTR_INC9 | 06.01.2020 | 5.47pm | Email | Loading of pipes into truck | Noise, Operating hours | 1. Raised concern of work activities prior to 7am 2. Noise from pipes being lowered into trucks for disposal | Incident investigated by Quarry Manager and formal response has been emailed. No works were undertaken prior to 7am and the pipes were loaded into truck at approximately 7.45am. Additional noise monitoring has been undertaken above the noise monitoring conditions of consent. | 14.02.2020
Liam Palmer | CTR_INC10 | 07.02.2020 | 12.10pm | Phone Call | Retaining wall piling | Noise | 1. Raised concern regarding noise from pile driving of retaining wall. | Advised it was a condition of consent to install sheet piling for retaining wall. Quarry Manager contacted acoustic consultant for advise and additional noise monitoring was requested. Discussed over phone advising of acoustic consultant site visit date and time to discuss concern. Advised unavailable to attend. Additional noise monitoring has been undertaken above the noise monitoring conditions of consent. | 14.02.2020
Shirley Davis | CTR_INC11 | 11.02.2020 | 12.52pm | Text Message | Retaining wall piling | Noise | 1. Raised concern regarding noise from pile driving of retaining wall. | Advised it was a condition of consent to install sheet piling for retaining wall. Quarry Manager contacted acoustic consultant for advise and additional noise monitoring was requested. Left Phone message advising of acoustic consultant site visit date and time to discuss concern. No response recieved. Additional noise monitoring has been undertaken above the noise monitoring conditions of consent. | 14.02.2020
Keiron Rochester | CTR_INC12 | 11.02.2020 | 6.22pm | Email | Retaining wall piling | Operating hours | 1. Raised concern over the pile driving for retaining wall ceased at 5.15pm and operating hours of consent were not adhered to. | Construction operating hours of consent are Mon_Fri 7.00am to 6.00pm. Works were completed at 5.15pm within the consent hours. Email response has been sent. | 14.02.2020
Kay Rochester | CTR_INC13 | 12.02.2020 | 9.07am | Text Message | Entrance construction and rolling | Vibration, Traffic | 1. Large vibrations at 8.30am in house 2. Video of truck carring pole excavator turned right out of driveway | Investigation undertaken by Quarry Manager found the following. 1. Vibration roller was undertaking standard road construction activities at entrance as per RMS construction guidelines. 2. Float carrying pile driver turned right due to the construction activities at the site entrance were restricting a safe left exit from site. Truck was under escort and eastbound traffic was temporarily stopped by escort vehicle during the turn to ensure safe passage. | 14.02.2020
Keiron Rochester | CTR_INC14 | 20.02.2020 | 6.15pm | Email | No activities on site | Noise | Approximately 3am this morning noise of a machine working was heard by local residents, coming from inside the quarry premises. | Investigated by Quarry Manager. Definitely no activity was being undertaken onsite as described. Email response sent. | 24.02.2020
Kay Rochester | CTR_INC15 | 30.03.2020 | 3.55pm | Text Message | Entrance construction and rolling | Vibration | Vibrations at 3.30pm in house | Investigation undertaken by Quarry Manager found the following. 1. Vibration roller was undertaking standard road construction activities at entrance as per RMS construction guidelines. Discussed with Robsons regarding alternatives to the activity but roller compaction is essential for the the intersection to be compliant. Return text sent advising roller status for upcoming weeks. Robsons advised to limit vibrator wherever possible. | 31.03.2020
Shirley Davis | CTR_INC16 | 30.03.2020 | 4.15pm | Phone | Entrance construction and rolling | Vibration, Noise | 1. Vibrations at 3.30am in house 2. Reversing beeper noise | Investigation undertaken by Quarry Manager found the following. 1. Vibration roller was undertaking standard road construction activities at entrance as per RMS construction guidelines. Discussed with Robsons regarding alternatives to the activity but roller compaction is essential for the the intersection to be compliant. Return text sent advising roller status for upcoming weeks. Robsons advised to limit vibrator wherever possible. 2. Found excavator with beeper. Advised contractor to replace with sqwauker. Interim measures put in place by contractor. | 31.03.2020
Keiron Rochester | CTR_INC17 | 14.04.2020 | 6.55am | Email | No Activities | Covid-19 Concern | Requesting shortening to operational hours due to Covid-19. | No change to operational hours. Newcastle Sand staying at original consent hours of operation even though legislation has passed allowing for extended construction hours. | 15.04.2020
Keiron Rochester | CTR_INC18 | 14.04.2020 | 6.55am | Email | Fencing, Concrete formwork | Noise | 1. Activities prior to 7.00am 2. Noise from chainsaw | Incident investigated by Quarry Manager. Only fencing setup work was being undertaken near 7.00am and the chainsaw was operated by Quarry Manger directly at 7.30 | 15.04.2020
Keiron Rochester | CTR_INC19 | 15.04.2020 | 7.09am | Email | Fencing, Concrete formwork | Noise | Reversing beepers. | No construction vehicles have beepers, they all have squaukers. | 15.04.2020
Keiron Rochester | CTR_INC20 | 21.04.2020 | 10.59am | Email | Street Lighting | Light | Street lighting effecting residence across the road. | Email response by MT, showing ammendments to the original management plan have reduced the light to the subject property. | 21.04.2020
Department of Planning, Industry & Environment - Complaint received by Keiron Rochester. | CTR_INC21 | 21.04.2020 | 1.01pm | Email | Sand Trial | Truck Movements | Complaint received regarding the truck movements prior to 9am during sand glass trial. | Currently under investigation. Response sent to DPIE. | 05.05.2020
Liam Rochester | CTR_INC22 | 23.04.2020 | 11.42am | Phone | Intersection Asphalting | Traffic turning right | Complained that trucks and vehicles were exiting the site by turning left. | Quarry manager investigated and found that the exit lane was blocked from the site due to hot asphalt being laid by Downer Group. Discussed with Robson supervisor and vehicles were exiting site under supervision of Drayton spotter via the entrance slipway due to safety concern of traffic turning left due to the exit angle. The only safe direction to exit the site was a right turn. | 23.04.2020
Keiron Rochester | CTR_INC23 | 24.04.2020 | 7.46am | Email | Intersection Construction | Truck Movements | Alledged trucks departing site loaded over previous two weeks in breach of consent. | Awaiting further details pertaining to the complaint from Mr Rochester. No additional information received from Mr Rochester. | 11.06.2020
Keiron Rochester | CTR_INC24 | 29.04.2020 | 6.17pm | Email | Intersection Construction | Potential Privacy Issue | Held in confidence due to the nature of the complaint. | Forwarded to Police currently under investigation. Police have advised no offence was committed. | 05.05.2020
Keiron Rochester | CTR_INC25 | 3.05.2020 | 5.03pm | Email | None | Traffic | Safety concern regarding concrete traffic island adjacent to front entrance. Requesting removal of traffic island. | Quarry Manager investigating documentation with key stakeholders. RMS has signed off the roadway compliant to construction requirements. | 01.06.2020
Liam Rochester | CTR_INC26 | 29.06.2020 | 11.00am | Phone | General site activities | Traffic | Reporting a safety concern regarding concrete traffic island adjacent to front entrance. Vehicle has just missed Kay as she was turning in to her driveway. Requesting removal of traffic island. | Issue of traffic Island raised at last CCC meeting. Newcastle Sand waiting on submission/letter from KR or community then Newcastle Sand will submit request to RMS.
Shirley Davis | CTR_INC27 | 23.07.2020 | 2.13pm | Text Message | N/A | Correspondance | Requesting paper copies of the last two CCC Meetings as previously agreed. | CCC Meeting minutes reprinted and placed in mailboxes. | 24.07.2020
Shirley Davis | CTR_INC28 | 17.08.2020 | 2.34pm | Text Message | N/A | Noise | Noise of air brakes of arriving and departing trucks | Rang freight control company regarding complaint and posted sign on weighbridge reinforcing requirement not to use engine braking. | 18.08.2020
CTR_INC29
CTR_INC30